## Prodcut Backlog
PRODUCT BACKLOG
Project BACKLOG REPORT
ID | AS A … | I WANT TO … | SO THAT … | PRIORITY | STATUS | STATUS | PRIORITY
1 | Student | View my class schedule | I know when my classes take place | High |  | Not Started | Low
2 | Student | Access learning materials | I can review and study lessons anytime | High |  | In Progress | Medium
3 | Student | Submit homework through the system | I can send my work to the teacher easily | High |  | Complete | High
4 | Student | View assignment deadlines | I can submit assignments on time | High |  | Overdue
5 | Student | Track my learning progress | I can understand my academic performance | Medium |  | On Hold
6 | Student | View teacher feedback | I can improve my learning | Medium
7 | Student | Check my attendance record | I know if I meet course requirements | Medium
8 | Teacher | View the list of students in my class | I know who I am teaching | High
9 | Teacher | Upload learning materials | students can access learning resources | High
10 | Teacher | Create assignments | students can practice what they learned | High
11 | Teacher | Review student homework submissions | I can evaluate their understanding | High
12 | Teacher | Provide feedback and grades | students know their performance | High
13 | Teacher | Record student attendance | participation is tracked in the system | Medium
14 | Teacher | Monitor student progress | I can support students who need help | Medium
15 | Admin | Create and manage user accounts | students and teachers can access the system | High
16 | Admin | Create and manage classes | courses are organized properly | High
17 | Admin | Assign teachers to classes | each class has an instructor | High
18 | Admin | Enroll students into classes | they can attend the appropriate courses | High
19 | Admin | Generate system reports | the center can evaluate attendance and performance | Low
20 | Admin | Manage course schedules | classes are arranged efficiently | High
21 |  |  |  | High
22 |  |  |  | High
23 |  |  |  | High
24 |  |  |  | High
25 |  |  |  | High
26 |  |  |  | High
27 |  |  |  | High
TOTAL

## Sprint 1 Blacklog
SPRINT 1 BACKLOG
SPRINT 1 BACKLOG REPORT
Sprint | User Story | Task | Owner | PRIORITY | STATUS | STATUS | PRIORITY
1 | As a student, I want to view my class schedule so that I know when my classes take place. | Design class schedule UI | UI Team |  |  | Not Started | Low
|  | Create schedule database table | DEV Team |  |  | In Progress | Medium
|  | Implement schedule viewing functionality | DEV Team |  |  | Complete | High
|  | Fetch schedule data from database | DEV Team |  |  | Overdue
|  | Write unit tests | TEST Team |  |  | On Hold
1 | As a student, I want to access learning materials so that I can review and study lessons anytime. | Design learning materials UI | UI Team
|  | Implement materials listing functionality | DEV Team
|  | Connect materials with database | DEV Team
|  | Implement download/view materials feature | DEV Team
|  | Write unit tests | TEST Team
1 | As a teacher, I want to view the list of students in my class so that I know who I am teaching. | Design student list interface | UI Team
|  | Create student list API | DEV Team
|  | Fetch student data from database | DEV Team
|  | Implement student list display | DEV Team
|  | Write unit tests | TEST Team
1 | As an admin, I want to create and manage user accounts so that students and teachers can access the system. | Design account registration form | UI Team
|  | Implement account creation functionality | DEV Team
|  | Validate input and display error messages | DEV Team
|  | Store user data in database | DEV Team
|  | Write unit tests | TEST Team
1 | As an admin, I want to create and manage classes so that courses are organized properly. | Design class management interface | UI Team
|  | Create class database structure | DEV Team
|  | Implement create/edit/delete class functions | DEV Team
|  | Connect class data to the system | DEV Team
|  | Write unit tests | TEST Team
TOTAL

## Bản sao của Sprint 1 Blacklog
SPRINT 1 BACKLOG
SPRINT 1 BACKLOG REPORT
ID | AS A … | I WANT TO … | SO THAT … | PRIORITY | STATUS | STATUS | PRIORITY
S1-US01 | Project Maneger | Create GitHub repository for the project | the team can collaborate effectively and track source code changes | High | Complete | Not Started | Low
S1-US02 | Project Maneger | Set up main branch (main/develop) | the team can collaborate effectively and track source code changes | High | Complete | In Progress | Medium
S1-US03 | Project Maneger | Write guidelines about branch, commit message, pull request | the team can collaborate effectively and track source code changes | High | In Progress | Complete | High
S1-US04 | Project Maneger | Configure access rights (collaborators) | the team can collaborate effectively and track source code changes | High | In Progress | Overdue
S1-US05 | Backend Developer | Install Node.js, React, Material UI, MySQL | we can start building applications with a standard platform | High | Complete | On Hold
S1-US06 | Backend Developer | Create directory structure for FE & BE | we can start building applications with a standard platform | High | In Progress
S1-US07 | Backend Developer | Set up environment configuration file (.env) for DB, port, ... | we can start building applications with a standard platform | High | Not Started
S1-US08 | Backend Developer | Test run basic application (run React at port 3000, Node at port 5000) | we can start building applications with a standard platform | High | Complete
S1-US09 | Business Analyst | Identify entities (Users, Articles, Vocabulary, ...) | the team has a clear and solid technical foundation for development | High | Not Started
S1-US10 | Business Analyst | Draw ERD diagram | the team has a clear and solid technical foundation for development | High | In Progress
S1-US11 | Business Analyst | Create DDL statements (CREATE TABLE) for main tables | the team has a clear and solid technical foundation for development | High | Not Started
S1-US12 | Business Analyst | Discuss with Dev to agree on fields, data types, constraints (FK, PK, etc.) | the team has a clear and solid technical foundation for development | High | Not Started
S1-US13 | Frontend Developer | Create React App | users can interact initially and the team has room to integrate features | Medium | Not Started
S1-US14 | Frontend Developer | Add Material UI, build layout (Header, Footer, Sidebar if any) | users can interact initially and the team has room to integrate features | Medium | Not Started
S1-US15 | Frontend Developer | Create basic routes (Home, Articles, Login, etc) | users can interact initially and the team has room to integrate features | Medium | Not Started
S1-US16 | Frontend Developer | Design temporary placeholder UI for main pages | users can interact initially and the team has room to integrate features | Medium | Not Started
S1-US17 | Backend Developer | Initialize NodeJS/Express app “Hello World” | backend is ready to integrate with frontend | High | Not Started
S1-US18 | Backend Developer | Create endpoint /login/ /register(POST) | backend is ready to integrate with frontend | High | Not Started
S1-US19 | Backend Developer | Create endpoint /articles(GET) to get list of articles from DB | backend is ready to integrate with frontend | High | Not Started
S1-US20 | Backend Developer | Test with Postman | backend is ready to integrate with frontend | High | Not Started
S1-US21 | Backend Developer | Create a separate folder/module for AI (eg: ai-services/) | I can integrate AI features in the following Sprints | Medium | Not Started
S1-US22 | Backend Developer | Install basic libraries (OpenAI, TensorFlow, HuggingFace, etc) | I can integrate AI features in the following Sprints | Medium | Not Started
S1-US23 | Backend Developer | Write example code or placeholder (eg: function summarizeText(text)) | I can integrate AI features in the following Sprints | Medium | Not Started
S1-US24 | Backend Developer | Make sure AI module can import/export to the rest | I can integrate AI features in the following Sprints | Medium | Not Started
S1-US25 | Project Maneger | Write test scenarios (test cases) for main flows: registration, login, reading articles | ensure all the components of the system are working smoothly before next Sprints | High | Not Started
S1-US26 | Project Maneger | Perform manual/automation testing | ensure all the components of the system are working smoothly before next Sprints | High | Not Started
S1-US27 | Project Maneger | Report bugs and track fix progress | ensure all the components of the system are working smoothly before next Sprints | High | Not Started
TOTAL